The project includes the reconstruction of a freeway interchange including bridge structures and ramps. This will be a multi-year multi-stage project to reconstruct the northbound lanes, ramps, and bridge structure the first year followed by the southbound lanes, ramps, and bridge structure the following year.

The contract includes interim completion dates for opening the ramps to traffic along with an interim date for completion of work before winter shutdown. These interim and final completion dates are as follows:

* Stage 2A – Open NB Ramps to Traffic: July 14, 2023
* Stage 2B – Open NB Lanes in Stage 3 Configuration: November 15, 2023
* Stage 4A – Open SB Ramps to Traffic: June 7, 2024
* Stage 4B – Project Completion: November 15, 2024

Utility conflicts exist in the areas of the SE and SW ramps. These utility conflicts must the relocated prior to ramp reconstruction. These utilities are scheduled to be relocated by May 1,2023.

The contractor has submitted the baseline schedule for acceptance. Review the attached reports and provide feedback comments for the schedule review. Utilize the baseline schedule review topics discussed and identify areas in which this baseline schedule can be improved.