## HMA Inspection Example
HMA Paving Inspection Form
Date: 6/15/17 | [5 empty] | Start Time: 7:00 am |  |  |  | Project ID: 1234-56-78
Paving Contractor: ABC Paving | [5 empty] | Finish Time: 3:30 pm |  |  |  | Roadway: STH 99
Inspected By: Joe Smith | [9 empty] | Weather: 70 & Sunny
Daily HMA Paving | [7 empty] | Temp Checks (F)
HMA Type: 4MT PG58-28H |  |  |  | Anticapted Tonaage: 1200 |  |  |  | Tonnage | STA | Truck | Hoper | Behind Paver
Lift: Lower |  |  |  | Actual Tonnage: 1237 |  |  |  | 22 | 10+10 | 300 | 291 | 260
Lanes: 1 |  |  |  | Density Determination: QMP |  |  |  | 50 | 11+90 | 280 | 273 | 253
Begin STA: 10+00 |  |  |  | Density Target: 91.0 |  |  |  | 168 | 12+50 | 290 | 278 | 258
End STA: 15+00 |  |  |  | Paving Thickness (IN): 2.5" |  |  |  | 500 | 13+01 | 297 | 288 | 268
Paving Width: 12' |  |  |  | Paving Thickness Loose (IN): 3.25" |  |  |  | 854 | 14+80 | 305 | 293 | 273
Mix Design: 250-000-000 |  |  |  | Cold Weather Paving: Y / N
NOTES: Paver broke down at sta 12+50
Yield
UNIT WT: |  | 110 LBS/SY/IN |  |  | Theo Calc= | ((a x b)/9) x (110 x c)) |  |  |  | Measured Thickns Loose (IN) | Measured Width After Compaction (FT) | Corrective Action
2000 LB/TON
Location |  |  |  | Width | Length | Thickns | Theo | Actual | Diff.
DIR | Lane | Begin STA | End STA | (FT) a | (FT) b | (IN) c | (TONS) | (TONS) | (TONS)
WB | 1 | 10+00 | 15+00 | 12 | 500 | 2 | 73.3333 | 78 | 4.6667 | 3.5 | 12.2 | Direct contractor to thin matt 1/8"
[10 empty] | 3.25 | 12
[10 empty] | 3.25 | 12.1
0
0
0
Yield
UNIT WT: |  | 110 LBS/SY/IN |  |  | Theo Calc= | ((a x b)/9) x (110 x c)) |  |  |  | Measured Thickns Loose (IN) | Measured Width After Compaction (FT) | Corrective Action
2000 LB/TON
Location |  |  |  | Width | Length | Thickns | Theo | Actual | Diff.
DIR | Lane | Begin STA | End STA | (FT) a | (FT) b | (IN) c | (TONS) | (TONS) | (TONS)
0
0
0
0
0
0
0
0
0

## HMA Inspection
HMA Paving Inspection Form
Date: | [5 empty] | Start Time: |  |  |  | Project ID:
Paving Contractor: | [5 empty] | Finish Time: |  |  |  | Roadway:
Inspected By: | [9 empty] | Weather:
Daily HMA Paving | [7 empty] | Temp Checks (F)
HMA Type: |  |  |  | Anticapted Tonaage: |  |  |  | Tonnage | STA | In Truck | In Hoper | Behind Paver
Lift: |  |  |  | Actual Tonnage:
Lanes: |  |  |  | Density Determination:
Begin STA: |  |  |  | Density Target:
End STA: |  |  |  | Paving Thickness (IN):
Paving Width: |  |  |  | Paving Thickness Loose (IN):
Mix Design: 250- |  |  |  | Cold Weather Paving: Y / N
NOTES:
Yield
UNIT WT: |  | 110 LBS/SY/IN |  |  | Theo Calc= | ((a x b)/9) x (110 x c)) |  |  |  | Measured Thickns Loose (IN) | Measured Width After Compaction (FT) | Corrective Action
2000 LB/TON
Location |  |  |  | Width | Length | Thickns | Theo | Actual | Diff.
DIR | Lane | Begin STA | End STA | (FT) a | (FT) b | (IN) c | (TONS) | (TONS) | (TONS)
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
Yield
UNIT WT: |  | 110 LBS/SY/IN |  |  | Theo Calc= | ((a x b)/9) x (110 x c)) |  |  |  | Measured Thickns Loose (IN) | Measured Width After Compaction (FT) | Corrective Action
2000 LB/TON
Location |  |  |  | Width | Length | Thickns | Theo | Actual | Diff.
DIR | Lane | Begin STA | End STA | (FT) a | (FT) b | (IN) c | (TONS) | (TONS) | (TONS)
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0