## CCO and Force Account
From Section 109.4.5 of the Standard Book of Specifications
Contract Modification Effort
A. Labor | Number | Daily Hours | Daily Hours | Total Hours | Hourly Rate | Total
|  |  |  | 0 |  | 0 | From Section 109.4.5.2 of the Standard Book of Specifications
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
[5 empty] | Subtotal | 0
A1. Payroll Additives
Workers Compensation |  |  |  | 12.75% | 0 | 0
Fed. Unemployment Comp |  |  |  | 0.8% | 0 | 0 | From Section 109.4.5.3 of the Standard Book of Specifications
State Unemployment Comp |  |  |  | 9.75% | 0 | 0
Social Security Tax |  |  |  | 7.65% | 0 | 0
[5 empty] | Subtotal | 0
A2. Fringe Benefits
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
[5 empty] | Subtotal | 0
[5 empty] | Total Labor | 0
B. Materials |  | Daily Quantity | Daily Quantity | Total Weekly Quantity | Rate/Unit
|  |  |  | 0 |  | 0 | From Section 109.4.5.4 of the Standard Book of Specifications
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
[5 empty] | Total Material | 0
C. Equipment | Number | Daily Hours | Daily Hours | Total Weekly Hours | Rate/Hour
|  |  |  | 0 |  | 0 | From Section 109.4.5.5 of the Standard Book of Specifications
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
[5 empty] | Total Equipment | 0
D. Insurance |  |  |  | Revenues |  | 0
|  |  |  | Markups from below |  | 0 | Force Account Only - If Applicable (Correct paperwork filed)
|  |  |  | Total Revenues for Property/Liability |  | 0 | From Section 109.4.5.3 of the Standard Book of Specifications
[5 empty] | Total Insurance | 0
Area A - Labor |  |  |  | Labor |  | 0
A. Per Section 109.4.5.2 |  |  |  | 35% of A + A2 |  | 0
A. Per Section 109.4.5.3 |  |  |  | 15% of A1 |  | 0
[5 empty] | Subtotal | 0
Area B - Materials |  |  |  | Materials |  | 0
B. Per Section 109.4.5.4 |  |  |  | 15% of B |  | 0
|  |  |  | 5.5% Sales Tax on B |  | 0
[5 empty] | Subtotal | 0
Area C - Equipment |  |  |  | Equipment |  | 0
[5 empty] | Subtotal | 0
Area D - Insurance |  |  |  | Public Liability
D. Per Section 109.4.5.3 |  |  |  | 15% of D
Subtotal
|  |  |  | Total Amount Due: |  | 0

## CCO EXAMPLE
Example - A 12 foot - 15" storm sewer line and a 3' deep, 2X3 inlet box has been found to need replacement on a mill and overlay project that has some curb repair and culvert replacements. The culvert crew is on site and close to the area of need. The prime contractor submitted a Contract Change Order price of $4000 and agreed to place base and asphalt surface at contract price. Is this acceptable?
Contract Modification Effort
A. Labor | Number | Daily Hours | Daily Hours | Total Hours | Hourly Rate | Total
Operator | 1 | 4 |  | 4 | 36.5 | 146
Laborer | 1 | 4 |  | 4 | 29 | 116
Laborer | 1 | 4 |  | 4 | 29 | 116 | Can be obtained from Special Provisions.
|  |  |  | 0 |  | 0
[5 empty] | Subtotal | 378
A1. Payroll Additives
Workers Compensation |  |  |  | 12.75% | 378 | 48.195
Fed. Unemployment Comp |  |  |  | 0.8% | 378 | 3.024
State Unemployment Comp |  |  |  | 9.75% | 378 | 36.855
Social Security Tax |  |  |  | 7.65% | 378 | 28.917
[5 empty] | Subtotal | 116.991
A2. Fringe Benefits
Operator | 1 |  |  | 4 | 20 | 80
Laborer | 1 |  |  | 4 | 14.5 | 58
Laborer | 1 |  |  | 4 | 14.5 | 58
[5 empty] | Subtotal | 196
[5 empty] | Total Labor | 690.991
B. Materials |  | Daily Quantity | Daily Quantity | Total Weekly Quantity | Rate/Unit
15" Concrete Pipe |  | 12 |  | 12 | 20 | 240
2X3 Inlet Box |  | 1 |  | 1 | 390 | 390 | Can Ask contractors for some information or contact suppliers.
Casting |  | 1 |  | 1 | 100 | 100
|  |  |  | 0 |  | 0
[5 empty] | Total Material | 730
C. Equipment | Number | Daily Hours | Daily Hours | Total Weekly Hours | Rate/Hour
CAT 330C excavator | 1 | 4 |  | 4 | 145 | 580
|  |  |  | 0 |  | 0 | Equipment Rates can be obtained from stacy.hangebucher@dot.wi.gov
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
[5 empty] | Total Equipment | 580
D. Insurance |  |  |  | Revenues
Markups from below
Total Revenues for Property/Liability
Total Insurance
Area A - Labor |  |  |  | Labor |  | 690.991
A. Per Section 109.4.5.2 |  |  |  | 35% of A + A2 |  | 200.9
A. Per Section 109.4.5.3 |  |  |  | 15% of A1 |  | 17.5487
[5 empty] | Subtotal | 909.4396
Area B - Materials |  |  |  | Materials |  | 730
B. Per Section 109.4.5.4 |  |  |  | 15% of B |  | 109.5
|  |  |  | 5.5% Sales Tax on B |  | 40.15
[5 empty] | Subtotal | 879.65
Area C - Equipment |  |  |  | Equipment |  | 580
[5 empty] | Subtotal | 580
Area D - Insurance |  |  |  | Public Liability
D. Per Section 109.4.5.3 |  |  |  | 15% of D
Subtotal
|  |  |  | Total Amount Due: |  | 2369.0896
Answer: Some incidentals that are not covered above would be availablity of getting storm sewer delivered, sawing of the area to dig through the trench, and if any additional traffic control would be required, but based on the above - the project leader should ask the contractor for justification of their price, talk with their project manager, and if needed go to force account if a price cannot be negotiated.