## Slide 1: Bureau of Project Development (BPD) Update
Matt Dapp
NW Region Construction Oversight Engineer
2019 NW Region Construction Training
Casper Conference Center, Eau Claire, WI
(Remote Locations – Spooner & Superior)
March 21, 2019

## Slide 2: Introduction
Experience
  WisDOT for 11+ years
    SW Region – Madison Office
    Previous 5 years as a project manager in PDS
      Managed both design and construction projects
      Dane, Columbia, Iowa & Lafayette Counties
    Served 1 year as SW Region Utility Engineer
    First 5 years spent as inspector/project leader on construction projects in Dane County

## Slide 3: Agenda
BPD Updates
When to Contact Construction Oversight Engineer
Contractor Schedules
Contract Modification Justification (CMJ)
Contract Change Order (CCO)
Project Disputes / Claims
Other Topics

## Slide 4: BPD Construction Standards Oversight Unit Updates
  Matt Dapp – NW Region
  Doak Christenson – SW Region
  Craig Pringle– NE Region
  Dave Pilon – NC Region
  Chris Fredrick – SE Region
  Brian DuPont – SE Freeways
  Michael Hall – Standard Specifications
  Mark Zander – CMM Updates
  Sandra Villiesse – Local Program

## Slide 5: When to Contact Construction Oversight Engineer?
All proposed cost reduction incentives (CRI)
  Include on CRI Tracking Form
Decisions that should be made at a statewide level
  Material shortages
  Cataclysmic phenomena of nature (extreme weather)
Potential claim issues
  Basis of entitlement
Questions with interpretation of contract specifications
Large-scale change orders/contract time extensions
Time extensions that may go over winter

## Slide 6: When to Contact Construction Oversight Engineer?
Issues with the standard specifications
Any submission of claim or notice of claim
Statewide consistency questions
  Assessing liquidated damages
A resource to bounce ideas off

## Slide 7: Contractor Schedules
Follow SS 108.4 Progress Schedules
  Verify baseline schedules
  Request narrative & other items
  Account for long lead procurement items
Require monthly updates
  Review and comment
  Avoid “implied consent”

## Slide 8: Contract Modification Justification (CMJ)
Documents must address:
  Scope (entitlement)
  Quality
  Time
  Cost
Written as a standalone document
  Include attachments for all references
  Should not have to refer to the plans & specials to understand
Should include an independent engineer’s estimate
  Do more than just confirm the price submitted from the contractor
  In theory, the CMJ should be written before you receive any pricing from the contractor

## Slide 9: Contract Change Order (CCO) (Contract Modification)
Cover all related issues in one CCO
  May require multiple CMJ’s
Be consistent within region
Commonly see:
  No additional contract time is provided by this contract modification
Replace with example in CMM 2-42 (Attachment 1):
  Additional contract time will not be provided to complete the work required and covered in the contract modification

## Slide 10: Project Disputes / Claims
Claim is an unresolved change or dispute resulting in a demand for additional cost, time, or both based on:
  Entitlement (why?)
  Impact (what or how?)
  Cost (how much?)
Ensure proper notification is given to allow department to mitigate
Read the contract as a whole to determine if there has been a change to the contract requirements (entitlement)
  Differing site conditions
  Suspensions of work ordered by the engineer
  Significant changes in the character of work
Separate original contract from claim cost
  Ask for contractor documents such as Job Cost Report that shows actual costs

## Slide 11: Other Topics
Detailed documentation
  Utilize laptops, iPads, etc.
Set expectations with contractor early and often
  Avoids issue of implied consent
Review Critical Inspection Guide
  Recent issues with beam guard posts & sign post embedment
Damage to contractor’s work
  Do not pay for damage to contractor’s work unless covered in contract (SS 107.14 Contractor’s Responsibility for Work)
Enforce the contract
  Consistency within the regions

## Slide 12: Questions?
Contact Information
Email: matthew.dapp@dot.wi.gov
Phone: (608) 266-3589
Cell: (608) 516-6481