## Example
Concrete Pavement Thickness Log
PROJECT DESCRIPTION | [6 empty] | GENERAL INFORMATION
Project |  |  |  | Contract |  |  | Tested By
| 1530-08-72 |  |  |  | 970221990 |  |  | John Geiger
Highway |  |  |  | County |  |  | Design Thickness |  |  | Construction Type
| STH15 |  |  |  | Dane |  |  | 11 |  | Mainline
Description | [6 empty] | Begin Station |  |  | Placement Technique
| CTH A - CTH B | [6 empty] | 98055 |  | Slip-Formed
Contractor | [6 empty] | End Station
| XYZ Construction Company | [6 empty] | 106000
Paving | Unit Location |  |  | Driving Lane Depth |  |  | Passing Lane Depth
Date | Begin | Probe | End | Right | Center | Avg * | Left | Center | Avg * | Comments
| Station | Station | Station | in | in | in | in | in | in
1996-09-25 | 98055 | 98100 | 98200 | 10.8 | 10.8 | 10.8 | 10.8 | 11 | 10.9
| 98200 | 98300 | 98400 | 10.8 | 11 | 10.9 | 11 | 11 | 11
| 98400 | 98500 | 98600 | 10.8 | 11.4 | 11 | 11 | 11.6 | 11.1
| 98600 | 98700 | 98800 | 11 | 11 | 11 | 11 | 11.2 | 11.1
| 98800 | 98900 | 99000 | 10.8 | 10.8 | 10.8 | 11 | 10.8 | 10.9
| 99000 | 99100 | 99200 | 10.8 | 10.8 | 10.8 | 10.8 | 11 | 10.9
| 99200 | 99300 | 99400 | 10.8 | 10.8 | 10.8 | 10.8 | 11 | 10.9
| 99400 | 99500 | 99600 | 10.8 | 11 | 10.9 | 11 | 11.2 | 11.1
| 99600 | 99700 | 99800 | 11.4 | 12.4 | 11.2 | 11.6 | 12.4 | 11.2
| 99800 | 99900 | 100000 | 10.8 | 10.8 | 10.8 | 10.8 | 11 | 10.9
| 100000 | 100100 | 100200 | 10.8 | 10.8 | 10.8 | 10.8 | 11 | 10.9
| 100200 | 100300 | 100400 | 11 | 11 | 11 | 11 | 11.2 | 11.1
| 100400 | 100500 | 100600 | 11.4 | 11 | 11.1 | 11 | 11.2 | 11.1
| 100600 | 100700 | 100800 | 11 | 11.4 | 11.1 | 11 | 11.6 | 11.1
| 100800 | 100900 | 101000 | 11 | 10.8 | 10.9 | 11 | 11 | 11
| 101000 | 101100 | 101200 | 11 | 11 | 11 | 10.8 | 11.2 | 11
1996-09-27 | 101200 | 101300 | 101400 | 11.4 | 11.4 | 11.2 | 11.4 | 11.8 | 11.2
| 101400 | 101500 | 101600 | 11 | 11 | 11 | 11.4 | 11.2 | 11.2
| 101600 | 101700 | 101800 | 10.8 | 11 | 10.9 | 11 | 11.2 | 11.1
| 101800 | 101900 | 102000 | 10.8 | 10.8 | 10.8 | 11 | 11.2 | 11.1
| 102000 | 102100 | 102200 | 11 | 11.2 | 11.1 | 11 | 11.4 | 11.1
| 102200 | 102300 | 102400 | 11.4 | 11.4 | 11.2 | 11 | 11.4 | 11.1
| 102400 | 102500 | 102600 | 11.4 | 11.2 | 11.2 | 10.8 | 11.2 | 11
| 102600 | 102700 | 102800 | 11.4 | 11.2 | 11.2 | 11.4 | 11.4 | 11.2
| 102800 | 102900 | 103000 | 11.4 | 11 | 11.1 | 11.2 | 11.2 | 11.2
| 103000 | 103100 | 103200 | 10.8 | 11.6 | 11 | 11.4 | 11.8 | 11.2
| 103200 | 103300 | 103400 | 10.8 | 11.4 | 11 | 11 | 11.4 | 11.1
| 103400 | 103500 | 103600 | 11 | 11.6 | 11.1 | 11.8 | 11.6 | 11.2
| 103600 | 103700 | 103850 | 10.8 | 10.8 | 10.8 | 11 | 11.2 | 11.1
* Individual probes greater than design +1/4" are considered design
+1/4" in the computation of the average depth

## Thickness Data
Concrete Pavement Thickness Log
PROJECT DESCRIPTION | [6 empty] | GENERAL INFORMATION
Project |  |  |  | Contract |  |  | Tested By (Name & Company)
Highway |  |  |  | County |  |  | Design Thickness (inches) |  |  | Construction Type
Description | [6 empty] | Begin Station |  |  | Placement Method
Paving Contractor | [6 empty] | End Station |  |  | Test Type (QC or QV)
Paving | Unit Location |  |  | Passing Lane Depth |  |  | Driving Lane Depth
Date | Begin | Random Test | End | Lt. WP | Rt. WP | Avg * | Lt. WP | Rt. WP | Avg * | Comments
| Station | Station | Station | in | in | in | in | in | in
* Individual depths greater than design +1/4" are considered design
+1/4" in the computation of the average depth