## Example Tracking
Mix Name | Example |  | PROJECT I.D. | Example
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
8/15/16 | 184+50-200+00 Curb & Gutter WB |  | 151 | 151 | yes |  |  | Pre- Placement Agg Test
816/16 | 175+00 to 350+00 Side Walk |  | 200 | 351 | yes |  |  | Date Received | 1/9/22
8/20/16 | 184+50-200+00 Curb & Gutter EB |  | 287 | 638 | yes |  |  | Report # | 501-A
8/21/16 | 200+00 to 400+00 Sidewalt |  | 51 | 689 | yes
9/13/16 | 200+00-400+00 Curb & Gutter EB |  | 275 | 964 | yes |  |  | * One tests per calender week
|  |  | TOTALS: | 964
Note on C6: Enter unit of measure.

## Example Testing Summary
Mix Design: Example
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Random # Cylinders | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 100 | 0.175, 17.5 CY | Air 6.0%, slump 2.5", temp 60 F | 0.254, 51 CY | 4400, 4250 | .789, 395 CY | Air: 6.0%, slump 3.0", temp 65 F, 4400,4700 psi
101 | 200 | 0.758, 177 CY | Air 6.0%, slump 2.5", temp 60 F
201 | 300 | 0.651, 266 CY | Air 6.0%, slump 2.5", temp 60 F | 0.654, 332 CY | 4150, 4800
301 | 400 | 0.235, 325 CY | Air 6.0%, slump 2.5", temp 60 F
401 | 500 | 0.358, 436 CY | Air 6.0%, slump 2.5", temp 60 F | 0.128, 427 CY | 4700, 4600
501 | 600 | 0.841, 585 CY | Air 6.0%, slump 2.5", temp 60 F |  |  | 0.473, 738 CY | Air: 6.0%, slump 3.0", temp 65 F, 4400,4700 psi
601 | 700 | 0.135, 615 CY | Air 6.0%, slump 2.5", temp 60 F | 0.749, 751 CY | 4060, 4200
701 | 800 | 0.467, 748 CY | Air 6.0%, slump 2.5", temp 60 F
801 | 900 | 0.962, 897 CY | Air 6.0%, slump 2.5", temp 60 F | 0.323, 966 CY | 4900, 4600
901 | 1000 | 0.631, 964 CY | Air 6.0%, slump 2.5", temp 60 F
1001 | 1100 |  |  |  |  | 0.321, 1162 CY
1101 | 1200
1201 | 1300
1301 | 1400
1401 | 1500
1501 | 1600
1601 | 1700
1701 | 1800
1801 | 1900
1901 | 2000
2001 | 2100
2101 | 2200
2201 | 2300
2301 | 2400
2401 | 2500
2501 | 2600
2601 | 2700
2701 | 2800
2801 | 2900
2901 | 3000
Comments:

## Mix Design #1
Mix Name |  |  | PROJECT I.D.
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Mix Design#1 Testing Summary
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Random # Cylinders | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 100
101 | 200
201 | 300
301 | 400
401 | 500
501 | 600
601 | 700
701 | 800
801 | 900
901 | 1000
1001 | 1100
1101 | 1200
1201 | 1300
1301 | 1400
1401 | 1500
1501 | 1600
1601 | 1700
1701 | 1800
1801 | 1900
1901 | 2000
2001 | 2100
2101 | 2200
2201 | 2300
2301 | 2400
2401 | 2500
2501 | 2600
2601 | 2700
2701 | 2800
2801 | 2900
2901 | 3000
Comments:

## Mix Design #2
Mix Name |  |  | PROJECT I.D.
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Mix Design#2 Testing Summary
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Random # Cylinders | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 100
101 | 200
201 | 300
301 | 400
401 | 500
501 | 600
601 | 700
701 | 800
801 | 900
901 | 1000
1001 | 1100
1101 | 1200
1201 | 1300
1301 | 1400
1401 | 1500
1501 | 1600
1601 | 1700
1701 | 1800
1801 | 1900
1901 | 2000
2001 | 2100
2101 | 2200
2201 | 2300
2301 | 2400
2401 | 2500
2501 | 2600
2601 | 2700
2701 | 2800
2801 | 2900
2901 | 3000
Comments:

## Mix Design #3
Mix Name |  |  | PROJECT I.D.
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Mix Design #3 Testing Summary
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Random # Cylinders | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 100
101 | 200
201 | 300
301 | 400
401 | 500
501 | 600
601 | 700
701 | 800
801 | 900
901 | 1000
1001 | 1100
1101 | 1200
1201 | 1300
1301 | 1400
1401 | 1500
1501 | 1600
1601 | 1700
1701 | 1800
1801 | 1900
1901 | 2000
2001 | 2100
2101 | 2200
2201 | 2300
2301 | 2400
2401 | 2500
2501 | 2600
2601 | 2700
2701 | 2800
2801 | 2900
2901 | 3000
Comments:

## Mix Design #4
Mix Name |  |  | PROJECT I.D.
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Mix #4 Testing Summary
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Random # Cylinders | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 100
101 | 200
201 | 300
301 | 400
401 | 500
501 | 600
601 | 700
701 | 800
801 | 900
901 | 1000
1001 | 1100
1101 | 1200
1201 | 1300
1301 | 1400
1401 | 1500
1501 | 1600
1601 | 1700
1701 | 1800
1801 | 1900
1901 | 2000
2001 | 2100
2101 | 2200
2201 | 2300
2301 | 2400
2401 | 2500
2501 | 2600
2601 | 2700
2701 | 2800
2801 | 2900
2901 | 3000
Comments:

## Mix Design #5
Mix Name | Example |  | PROJECT I.D. | Example
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Design #5 Testing Summary
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Random # Cylinders | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 100
101 | 200
201 | 300
301 | 400
401 | 500
501 | 600
601 | 700
701 | 800
801 | 900
901 | 1000
1001 | 1100
1101 | 1200
1201 | 1300
1301 | 1400
1401 | 1500
1501 | 1600
1601 | 1700
1701 | 1800
1801 | 1900
1901 | 2000
2001 | 2100
2101 | 2200
2201 | 2300
2301 | 2400
2401 | 2500
2501 | 2600
2601 | 2700
2701 | 2800
2801 | 2900
2901 | 3000
Comments:

## Deck Overlay Mix Design #1
Mix Name | Example |  | PROJECT I.D. | Example
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Deck Overlay Testing Summary #1
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Cylinder results (PSI) | Aggregate Random # | Random # (air, slump, temp, cylinders) | Results
0 | 50
51 | 100
101 | 150
151 | 200
201 | 250
251 | 300
301 | 350
351 | 400
401 | 450
451 | 500
501 | 550
551 | 600
601 | 650
651 | 700
701 | 750
751 | 800
801 | 850
851 | 900
901 | 950
951 | 1000
1001 | 1050
1051 | 1100
1101 | 1150
1151 | 1200
1201 | 1250
1251 | 1300
1301 | 1350
1351 | 1400
1401 | 1450
1451 | 1500
Comments:

## Deck Overlay Mix Design #2
Mix Name | Example |  | PROJECT I.D. | Example
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | Agg Tests* | REMARKS
Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Deck Overlay Testing Summary(2)
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Cylinder results (PSI) | Aggregate Random # | Random # (air, slump, temp, cylinders) | Results
0 | 50
51 | 100
101 | 150
151 | 200
201 | 250
251 | 300
301 | 350
351 | 400
401 | 450
451 | 500
501 | 550
551 | 600
601 | 650
651 | 700
701 | 750
751 | 800
801 | 850
851 | 900
901 | 950
951 | 1000
1001 | 1050
1051 | 1100
1101 | 1150
1151 | 1200
1201 | 1250
1251 | 1300
1301 | 1350
1351 | 1400
1401 | 1450
1451 | 1500
Comments:

## Base Mix Design (1)
Mix Name | Example |  | PROJECT I.D. | Example
Mix Description |  |  | ROADWAY
Placement Method |  |  | DESCRIPTION
Concrete Yardage (Estimate Only) |  |  | COUNTY
CY
DATE | Location |  | CY | SUBTOTAL | WS5013 | QC Agg Tests* | REMARKS
QC Pre- Placement Agg Test
Date Received
Report #
* One tests per calender week
|  |  | TOTALS: | 0
Note on C6: Enter unit of measure.

## Base Summary (1)
Mix Design:
Total CY Placed:
Cubic Yards |  | QC Tests |  |  | QV tests
Start | End | Random # (air, slump, temp) | Results | Cylinder results (PSI) | Random # (air, slump, temp, cylinders) | Results
0 | 250
251 | 500
501 | 750
751 | 1000
1001 | 1250
1251 | 1500
1501 | 1750
1751 | 2000
2001 | 2250
2251 | 2500
2501 | 2750
2751 | 3000
3001 | 3250
3251 | 3500
3501 | 3750
3751 | 4000
4001 | 4250
4251 | 4500
4501 | 4750
4751 | 5000
5001 | 5250
5251 | 5500
5501 | 5750
5751 | 6000
6001 | 6250
6251 | 6500
6501 | 6750
6751 | 7000
7001 | 7250
7251 | 7500
* One test per 400 CY/max one test per day
Comments: