## Directions
Additional Notes/Directions
Mix Tab
● | Create new tabs for each mix design
● | Label the tabs with the mix design number
● | Fill in project information
● | Ensure the tons of fly ash pre-set calculation is correct
| ◦ | If it is not - please change the amount of fly ash to match the mix design
● | Feel free to make adjustments to the columns as necessary
● | Be sure to check ASP 6 and the special provisions to make sure testing frequencies aren't changed
Aggregates-Class I Tab
● | Number of required tests is pre-set depending on the daily quantity
| ◦ | Please make adjustments to the required tests if there is an RFI for the project
| ◦ | If there is an RFI - make note of it in the tracking form
● | Be sure to check ASP 6 and the special provisions to make sure testing frequencies aren't changed
● | Concrete mixes that have the same aggregate proportions can be tracked together
Aggregates-Class II Tab
● | Number of required tests is not preset since the frequency is 1/week
| ◦ | Please see the Example-Aggs Class II
● | Be sure to check ASP 6 and the special provisions to make sure testing frequencies aren't changed
● | Concrete mixes that have the same aggregate proportions can be tracked together

## Mix #1
Mix Testing, QMP [QMP Type] - [Contractor] - [Mix Number]
|  | Project ID: |  |  |  |  | Concrete Supplier: |  |  |  | QC Frequencies:
|  | Project Description |  |  |  |  | Mix Design Number |  |  |  | QV Frequencies:
|  | Bid Item(s): |  |  |  |  | Concrete Grade: |  |  |  | Small Quantities?
|  | Notes (e.g. Lot Number) |  |  |  |  | Fly Ash/Slag Source:
|  | Estimated Quantity: |  |  |  |  | Pour Location(s):
Date | CY Quantity | Cumm. Qty | Tons Fly Ash/Slag | QC Testing | [7 empty] | QV Testing | [7 empty] | Comments/Location of Pour/Nonconforming Tests
|  |  |  | QC Field Report Received | # of Random QC Tests | Lot-Sublot | Random Number | Random Location | CY Test Frequency | Average Strength | Surface Resistivity/Other | # of QV Tests | Lot-Sublot | Random Number | Random Location | Represents # of QC | Average Strength | 130 Test Number | Surface Resistivity/Other
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0

## Aggregates
Aggregate Tracking & Testing, [QMP Type] - [Concrete Supplier] - [Mix Design(s)]
|  | Project ID: |  |  |  | Mix Design Number(s): |  |  | QC Frequency:
|  | Project Description |  |  |  | Coarse Agg Source(s): |  |  | QV Frequency:
|  | Concrete Supplier: |  |  |  | Fine Agg Source: |  |  | Small Quantity?:
|  | Plant Location: |  |  |  | *Date of Initial Agg Test:
*must be within 5 days of placement
Date | CY | Cumm. CY | QC Testing |  |  |  | QV Testing
|  |  | Grad. Tests Required | Grad. Tests Completed | Test Frequency | Results | Grad. Tests Completed | Test Frequency | 162 Test Number | Results | Notes/Location of Pour/Nonconforming Tests
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Example-Mix Class I Structures
Mix Testing, QMP Structures - Lunda - 4783
|  | Project ID: | 1060-33-84 |  |  |  | Concrete Supplier: | Ozinga |  |  | QC Frequencies: | 1/50 CY
|  | Project Description | Zoo NL |  |  |  | Mix Design Number | 4783 |  |  | QV Frequencies: | 1/Lot
|  | Bid Item(s): | 502.01 |  |  |  | Concrete Grade: | A |  |  | Small Quantities? | No
|  | Lot Number(s): | Lot 1 & 2 |  |  |  | Fly Ash/Slag Source: | Ozinga-Joppa
|  | Estimated Quantity: | 850 CY |  |  |  | Pour Location(s): | B-40-793
|  | Lot/Sublot Size: | 250 CY/50 CY |  |  |  | Notes: | SAM testing not required
Date | CY Quantity | Cumm. Qty | Tons Fly Ash/Slag | QC Testing | [7 empty] | QV Testing | [7 empty] | Comments/Location of Pour/Nonconforming Tests
|  |  |  | QC Field Report Received | # of Random QC Tests | Lot-Sublot | Random Number | Random Location (CY) | CY Test Frequency | Average Strength | Surface Resistivity/Other | # of QV Tests | Lot-Sublot | Random Number | Random Location | Represents # of QC | Average Strength | 130 Test Number | Surface Resistivity/Other
2024-06-10 | 189 | 189 | 16.065 | X | 3 | 1-1 1-2 1-3 | 0.215 0.987 0.554 | 11 99 128 | 0-50 50-100 100-150 | 4899 5237 5102 | 1 Resistivity | 1 | 1-2 | 0.289 | 64 | Lot 1-1 thru 1-5 | 4965 | 2-130-0001-2024 | 1 Resistivity | B-40-793
2024-06-11 | 44 | 233 | 19.805 | X | 2 | 1-4 1-5 | 0.598 0.377 | 180 219 | 150-200 200-250 | 5065 4945 | 1 Resistivity | - | - | - | - | - | - |  | - | B-40-793
2024-06-14 | 15 | 248 | 21.08 | X | - | - | - | - | - | - | -
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08
|  | 248 | 21.08

## Example-Aggs Class I Structures
Aggregate Tracking & Testing, QMP Class I, Structures - Ozinga - 4783
|  | Project ID: | 1060-33-84 |  |  | Mix Design Number(s): | 4783 & 5232 |  | QC Frequency: | 1/150 CY, maximum of one test per day
|  | Project Description | Zoo NL |  |  | Coarse Agg Source(s): | Lannon |  | QV Frequency: | 1/250 CY & 1 per sub & super structure
|  | Concrete Supplier: | Ozinga |  |  | Fine Agg Source: | Lannon |  | Small Quantity?: | No
|  | Plant Location: | West Allis |  |  | *Date of Initial Agg Test: | 2024-06-07
*must be within 5 days of placement
Date | CY | Cumm. CY | QC Testing |  |  |  | QV Testing
|  |  | Cumm. Grad. Tests Required | Grad. Tests Completed | Test Frequency | Results | Grad. Tests Completed | Test Frequency | 162 Test Number | Results | Notes/Location of Pour/Nonconforming Tests
2024-06-10 | 189 | 189 | 1 | 1 | 0-150 CY | Pass | - | - | - | - | B-40-793
2024-06-11 | 44 | 233 | 1 | 1 | 150-300 CY | Pass | 1 | 0-250 CY | 2-162-0001-2024 | Pass | B-40-793
2024-06-14 | 15 | 248 | 0 | 0 | - | - | - | - | - | - | B-40-793
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248
248

## Example-Aggs Class II Base
Aggregate Tracking & Testing, QMP Ancillary Class II, Concrete Base - Zignego - P2 910
|  | Project ID: | 1060-33-84 |  |  | Mix Design Number(s): | P2 910 |  | QC Frequency: | 1/day if < 1000 CY per day
|  | Project Description | Zoo NL |  |  | Coarse Agg Source(s): | Lannon |  | QV Frequency: | No minimum
|  | Concrete Supplier: | Zignego |  |  | Fine Agg Source: | Lannon |  | Small Quantity?: | No
|  | Plant Location: | West Allis |  |  | *Date of Initial Agg Test: | 2025-07-06
*must be within 5 days of placement
Date | CY | Cumm. CY | QC Testing |  |  |  | QV Testing
|  |  | Grad. Tests Required | Grad. Tests Completed | Test Frequency | Results | Grad. Tests Completed | Test Frequency | 162 Test Number | Results | Notes/Location of Pour/Nonconforming Tests
2025-07-08 | 11 | 11 | 1 | - | 1/week | Pass | - | - | - | -
2025-08-10 | 13 | 24 | 1 | 1 | 1/week | Pass | - | - | - | -
2025-08-11 | 15 | 39 |  |  |  |  | - | - | - | -
2025-09-01 | 14 | 53 | 1 | - | 1/week | Pass | - | - | - | -
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53
53