## Directions
Additional Notes/Directions
Mix Tab
● | Create new tabs for each mix design
● | Label the tabs with the mix design number
● | Fill in project information
● | Feel free to make adjustments to the columns as necessary
| ◦ | If using this tracking sheet for Acceptance jobs, please remove the QC columns since testing is based on department testing.
● | Be sure to check ASP 6 and the special provisions to make sure testing frequencies aren't changed

## Mix #1
TESTING SUMMARY FOR [WISDOT MIX # (CONTRACTOR MIX #)]
| Project ID: | [5 empty] | WisDOT Mix Number: |  |  | AC Type:
| Project Description | [5 empty] | Contractor Mix Number: |  |  | Plan Quantity:
Plant Location:
Date | Location | Qty (Ton) | Cumm. Qty (Ton) | QC Mix Testing |  |  |  |  | QV Mix Testing |  |  |  |  | Comments | DENSITY TESTING SUMMARY - [WisDOT Mix Number]
|  |  |  | Req'd QC Mix Tests | QC Mix Tests Performed | Air Voids | Random No. | Random Tons | QV Mix Tests Performed | Random No. | Random Tons | Test Frequency | WisDOT Test Number/Results |  | Date | Lot ID | Sublot ID | Original LF/Lot | Original Tons/Lot | QC Tests |  |  |  | QV Tests |  |  | Approved in Atwoods? | Incentive/ Disincentive? | Paid in Estimate #
|  |  | 0 | [16 empty] | # of Tests Req'd | # of Tests Completed | Required Density | Actual Density | # of Tests Completed | MITS Test Number | Results
0
0
0
0
0

## Example, 0-250-0123-2020
TESTING SUMMARY FOR [WISDOT MIX # (CONTRACTOR MIX #)]
| Project ID: | [5 empty] | WisDOT Mix Number: |  |  | AC Type:
| Project Description | [5 empty] | Contractor Mix Number: |  |  | Plan Quantity:
Plant Location:
Date | Location | Qty (Ton) | Cumm. Qty (Ton) | QC Mix Testing |  |  |  |  | QV Mix Testing |  |  |  |  | Comments | DENSITY TESTING SUMMARY - [WisDOT Mix Number]
|  |  |  | Req'd QC Mix Tests | QC Mix Tests Performed | Air Voids | Random No. | Random Tons | QV Mix Tests Performed | Random No. | Random Tons | Test Frequency | WisDOT Test Number/Results |  | Date | Lot ID | Sublot ID | Original LF/Lot | Original Tons/Lot | QC Tests |  |  |  | QV Tests |  |  | Approved in Atwoods? | Incentive/ Disincentive? | Paid in Estimate #
2022-08-05 | North Ave EB, STA 117NO+10 to 120NO+50 | 328.01 | 328.01 | 1 | 1 | 2.8 | 0.335 | 94 | - | - | - | - | - | - | [5 empty] | # of Tests Req'd | # of Tests Completed | Required Density | Actual Density | # of Tests Completed | MITS Test Number | Results
2022-09-13 | North Ave WB, STA 117NO+10 to 120NO+50 & STA 164TX+08 to 167TX+25, LT/RT | 429.68 | 757.69 | 1 | 1 | 3.1 | 0.287 | 115 | - | - | - | - | - | - | 2022-08-05 | 19-ML-L1 | N/A - planned random numbers did not occur at the location paved this day | [6 empty] | - | - | - | Yes | 0 | -
2022-09-21 | North Ave Stage 2 Binder Lanes EB & WB & STA 164TX+08 to 167TX+25, LT/RT | 2400.8 | 3158.49 | 3 | 3 | 2.7 3.0 2.9 | 0.197 0.637 0.385 | 118 1173 1731 | 1 | 0.641 | 3205 | 0-5000 Tons | 2-254-0218-2022 Pass | - | 2022-09-13 | 20-SR-L1 | 13 | 361 | 39 | 1 | 2 | 91% | 91.4% | - | - | - | Yes | 0 | -
2022-09-22 | North Ave Stage 2 Binder Lanes WB & STA 160TX+00 to 162TX+75, LT/RT | 1176.36 | 4334.85 | 2 | 2 | 2.6 3.2 | 0.902 0.045 | 541 623 | - | - | - | - | - | - | 2022-09-21 | 22-ML-L1 | N-16 | 2125 | 558 | 3 | 3 | 91% | 93.4% | 3 | 095.650-262-0303-2022 | Satisfactory | Yes | 757.76 | 44
2022-10-09 | Mayfair Rd - Storm Sewer Crossing | 135.87 | 4470.72 | 1 | 1 | 3.3 | 0.987 | 59 | - | - | - | - | - | - |  |  | N-17 | 2125 | 558 | 3 | 3 | 91% | 92.9% | - | - | -
2022-11-11 | North Ave EB STA 109NO+60 to 116NO+00 | 249.83 | 4720.55 | 1 | 1 | 3.1 | 0.335 | 80 | - | - | - | - | - | - |  |  | N-18 | 2125 | 558 | 3 | 3 | 91% | 91.7% | - | - | -
[17 empty] | N-7 | 708 | 184 | 3 | 1* | 91% | 91% | - | - | -
[17 empty] | N-8 | 708 | 184 | 3 | 1* | 91% | 92% | - | - | -
[16 empty] | 22-SR-L1 | 20 | 81 | 41 | 1 | 1 | 91% | 94.1% | 1 | 095.650-262-0305-2022 | Satisfactory | Yes | 64.8 | 44
[17 empty] | 22 | 62 | 35 | 1 | 1 | 91% | 93.9% | 1 | 095.650-262-0307-2022 | Satisfactory
[16 empty] | 22-TL-L1 | 19 | 241 | 63 | 1 | 1 | 91% | 93.9% | 1 | 095.650-262-0304-2022 | Satisfactory | Yes | 134.76 | 44
[17 empty] | 21 | 313 | 82 | 1 | 1 | 91% | 94.6% | 1 | 095.650-262-0306-2022 | Satisfactory
[17 empty] | 23 | 233 | 61 | 1 | 1 | 91% | 90.9% | - | - | -
[17 empty] | 24 | 212 | 56 | 1 | 1 | 91% | 91.3% | - | - | -
[17 empty] | 25 | 365 | 96 | 1 | 1 | 91% | 91.4% | - | - | -
[15 empty] | 2022-09-22 | 23-ML-L1 | N-7 | 1025 | 292 | 3 | 2* | 91% | 93.6% | 3 | 095.650-262-0309-2022 | Satisfactory | Yes | 348.24 | 44
[17 empty] | N-8 | 1025 | 292 | 3 | 2* | 91% | 93.2% | 3 | 095.650-262-0308-2022 | Satisfactory
[17 empty] | N-9 | 1000 | 286 | 2 | 2* | 91% | 91.7% | - | - | -
[16 empty] | 23-SR-L1 | 17 | 275 | 96 | 1 | 1 | 91% | 91.8% | 3 | 095.650-262-0314-2022 | Satisfactory | Yes | 0 | -
[17 empty] | 11 | 275 | 132 | 1 | 1 | 91% | 90.8% | - | - | -
[17 empty] | 12 | 155 | 17 | 1 | 1 | 91% | 92.8% | - | - | -
[16 empty] | 23-SH-L1 | 18 | 361 | 54 | 1 | 1 | 91% | 91.7% | 3 | 095.650-262-0315-2022 | Satisfactory | Yes | 0 | -
[15 empty] | 2022-10-09 | 25-L1 | Density Testing Waived Since < 50' Long
[15 empty] | 2022-11-11 | 32-ML-L1 | N-9 | 2125 | 221 | 1 | 1* | 91% | 92% | - | - | - | - | - | -
Notes *remaining tests are performed on the next day (9/22/2022)